## Sheet1
Steps
2020-03-21 | Sat | Define project scope, find datasources | 1 | Scope
2020-03-22 | Sun | Get all the other sources we need (school calendars, weather, etc.) | 2 | Identify Data source
2020-03-23 | Mon | Call Transtart, get access to the data! | 3 | Obtain access to data source
2020-03-24 | Tue | ETL | 4 | ETL
2020-03-25 | Wed | Python Analysis | 5 | Python analysis
2020-03-26 | Thu | Predictive Models | 6 | Build predictive models
2020-03-27 | Fri | Flask | 7 | Flask application to return model results
2020-03-28 | Sat | AWS | 8 | Deploy on AWS
2020-03-29 | Sun | Dashboard | 9 | Develop dashboard
2020-03-30 | Mon | Visualizations | 10 | Create visualizations
2020-03-31 | Tue | Overflow, work on presentation | 11 | Presentation
2020-04-01 | Wed | Practice/Finalize Presentation
2020-04-02 | Thu | Presentation